## Checkout Process Testing
ID | Title | Description | Comment
1 | Test Plan Identifier | - Project Name: E-Commerce System - Module: Checkout Process - Version: 1.0 - Prepared By: Mohamed Abdulaziz - Date: 27 Feb 2026
2 | Objectives | - The objective of this test plan is to validate the end-to-end checkout process and ensure that users can successfully complete a purchase flow from adding items to the cart until receiving order confirmation - The test plan covers the following checkout stages: - Adding items to cart - User authentication - Applying discount - Entering shipping details - Payment via third-party gateway - Order confirmation
3 | Scope | - In Scope - The following areas are included in this test plan: 1. Cart Management: - Add item(s) to cart - Update cart contents - Remove item(s) from cart - Validate cart totals before checkout 2. User Authentication: - Login before checkout (if required) - Guest vs registered user behavior (if supported) - Session continuity during checkout 3. Discount Application: - Apply valid discount/coupon code - Reject invalid or expired discount code - Validate discount calculation - Validate discount impact on final order total 4. Shipping Details: - Enter valid shipping information - Validate mandatory fields - Validate incorrect/invalid formats - Verify shipping method selection if applicable 5. Payment: - Redirect/initiate payment through third-party gateway - Successful payment flow - Failed payment flow - Cancelled payment flow - Return from payment gateway to merchant platform 6. Order Confirmation: - Successful order placement - Order confirmation page/message - Order summary accuracy - Confirmation email/SMS if applicable
| Out of Scope | - Unless explicitly supported by the system, the following are considered out of scope: - Warehouse/inventory backend processing - Refund processing - Order shipment tracking - Loyalty program behavior not directly related to checkout - Performance/load testing in production-like scale - Security penetration testing
4 | Test Approach | - Testing will be performed using manual functional testing supported by exploratory testing for related edge cases - Testing Types Included: - Functional Testing - End-to-End Testing - Integration Testing - Negative Testing - Boundary Testing - UI/UX Validation - Data Validation - Exploratory Testing - Regression-focused validation for critical checkout flow
| Test Design Basis | - The test scenarios will be designed based on: - Business requirements - Checkout process flow - Input validation rules - Expected user behavior - Error handling and recovery scenarios
5 | Test Items / Modules to be Tested | - The checkout process will be divided into the following modules: - Cart Module - Authentication Module - Discount Module - Shipping Details Module - Payment Gateway Integration - Order Confirmation Module
6 | Entry Criteria | - Testing can start when: - The checkout flow is available in the test environment - Required test accounts are available - Test products are available and purchasable - Payment integration is accessible in test/sandbox mode - Discount/coupon test data is available - Shipping form and order confirmation page are implemented
7 | Exit Criteria | - Testing will be considered complete when: - All critical checkout scenarios are executed - All high-priority defects are reported - Critical blockers preventing checkout completion are resolved or documented - Core positive and negative scenarios are covered - Test results are reviewed and documented
8 | Assumptions | - The following assumptions are made for this plan: - Users can add one or more items to the cart before checkout - Authentication may be required before payment completion - Discount codes can affect order totals - Shipping details are required before payment - Payment is processed through a third-party provider - Successful payment leads to order confirmation
9 | Risks | - Third-party payment provider instability - Invalid or incomplete discount setup - Environment issues affecting login or payment callbacks - Test data not matching business scenarios - Session timeout during checkout
| Dependencies | - Availability of checkout environment - Availability of valid and invalid discount codes - Availability of payment gateway sandbox/test credentials - Availability of test products and user accounts
10 | Test Data Requirements | - The following test data should be prepared: 1. User Data: - Valid registered user - Invalid user credentials - Locked/inactive user if applicable 2. Cart Data: - Single item order - Multiple item order - Empty cart - High-value cart if applicable 3. Discount Data: - Valid discount code - Invalid discount code - Expired discount code - Already-used discount code (if applicable) 4. Shipping Data: - Valid shipping address - Missing mandatory fields - Invalid postal code / phone / address format - Unsupported shipping region if applicable 5. Payment Data: - Successful payment card/account - Declined payment card/account - Cancelled payment scenario - Timeout/interruption scenario if supported
11 | High-Level Test Scenarios | A. Cart Scenarios: - Verify user can add one item to cart - Verify user can add multiple items to cart - Verify user can remove item(s) from cart - Verify user cannot proceed to checkout with an empty cart - Verify cart subtotal is calculated correctly
B. Authentication Scenarios: - Verify registered user can log in and continue checkout - Verify invalid login prevents checkout continuation - Verify user session remains active during checkout - Verify cart contents persist after login if expected
C. Discount Scenarios: - Verify valid discount code is applied successfully - Verify invalid discount code is rejected - Verify expired discount code is rejected - Verify discount amount is reflected correctly in order summary - Verify total amount is recalculated correctly after discount
D. Shipping Details Scenarios: - Verify user can enter valid shipping details - Verify mandatory shipping fields are enforced - Verify invalid field formats are rejected - Verify user cannot continue with incomplete shipping details
E. Payment Scenarios: - Verify user is redirected to the third-party payment provider - Verify successful payment returns the user to the platform correctly - Verify declined payment is handled correctly - Verify cancelled payment returns the user with proper status/message - Verify payment interruption does not create invalid orders
F. Order Confirmation Scenarios: - Verify successful checkout displays order confirmation page - Verify order summary is correct after successful payment - Verify order ID/reference is generated if applicable - Verify confirmation notification is triggered if applicable
12 | Non-Functional Considerations | - Although this plan mainly focuses on functional behavior, the following should also be observed during testing: - Clarity of validation messages - UI consistency across checkout steps - Navigation consistency - Response time of major actions - Reliability of payment redirection and callback handling
13 | Defect Management | - All defects found during execution should be documented with: - Defect ID - Title - Module - Preconditions - Steps to reproduce - Expected result - Actual result - Severity - Priority - Screenshot
14 | Deliverables | - The expected deliverables for this task are: - Checkout Test Plan document - Related test scenarios / test cases if required - Bug reports for identified issues - Supporting screenshots if available
| Conclusion | This test plan ensures broad and structured coverage of the full checkout journey, including both positive and negative flows. The focus is to validate that the user can complete the checkout process accurately, securely, and reliably from cart creation until final order confirmation.